## MS Project Data
Tasks | All
Data
Year | Cost | Cumulative Cost
2024 | 675200 | 675200
2025 | 4042752 | 4717952
2026 | 1759296 | 6477248
2027 | 1306602.5 | 7783850.5
2028 | 138373.06 | 7922223.5556
2029 | 219540 | 8141763.5556
2030 | 1625279.44 | 9767043
2031 | 373117.56 | 10140160.5581
2032 | 3892536.1033 | 14032696.6658
2033 | 1526631.3367 | 15559328
Grand Total | 15559328 | 15559328

## Sheet1
|  |  | OPTIMISTIC: NO OVERRUNS |  |  | PESSIMISTIC: 20% OVERRUNS
Year | Year | Optimistic cumulative project cost | Optimistic funding needed | Optimistic cumulative funding | Remaining cash flow | Pessimistic project cost | Pessimistic cumulative funding needed | Remaining cash flow
| 2024 | -675200 | 4000000 | 4000000 | 3324800 | -810240 | 4800000 | 3989760
| 2025 | -4717952 | 1000000 | 5000000 | 282048 | -5661542.4 | 6000000 | 338457.6
| 2026 | -6477248 | 2000000 | 7000000 | 522752 | -7772697.6 | 8400000 | 627302.4
| 2027 | -7783850.5 | 1000000 | 8000000 | 216149.5 | -9340620.6 | 9600000 | 259379.4
| 2028 | -7922223.5556 | 1000000 | 9000000 | 1077776.4444 | -9506668.2667 | 10800000 | 1293331.7333
| 2029 | -8141763.5556 | 1000000 | 10000000 | 1858236.4444 | -9770116.2667 | 12000000 | 2229883.7333
| 2030 | -9767043 | 1000000 | 11000000 | 1232957 | -11720451.6 | 13200000 | 1479548.4
| 2031 | -10140160.5581 | 1000000 | 12000000 | 1859839.4419 | -12168192.6697 | 14400000 | 2231807.3303
| 2032 | -14032696.6658 | 3000000 | 15000000 | 967303.3342 | -16839235.999 | 18000000 | 1160764.001
| 2033 | -15559328 | 1000000 | 16000000 | 440672 | -18671193.6 | 19200000 | 528806.4

## Compatibility report
Compatibility Report for adr8.xlt
Run on 16/09/2024 19:37
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Significant loss of functionality | # of occurrences | Version
Some formatting on charts in this workbook is not supported in earlier versions of Excel and will not be displayed. | 3 | Excel 97-2003
A PivotTable or data connection in this workbook contains server settings which do not exist in earlier versions of Excel. Some PivotTable or data connection server settings will not be saved. | 1 | Excel 97-2003
Excel 2007
Minor loss of fidelity
A PivotTable in this workbook will not work in versions prior to Excel 2007. Only PivotTables that are created in Compatibility Mode will work in earlier versions of Excel. | 1
| Task Usage'!A1:C15 | Excel 97-2003
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 14 | Excel 97-2003